## Scope
DeepHealth Phase 3.1
Scope item | Description | Questions | Comments
Platfrom Foundation | Gleamer user onboarding to nova required configuration, enviorments, Devops | Who are the Gleamer users? What Salesforce license does each user need? Which environment will be used for development, testing/UAT and production? What Gleamer Salesforce configuration needs to be retained? What licenses and third-party access are required? How will deployment and rollback be handled? | Set up the Salesforce foundation properly before starting the actual migration/build. Pasted text
Security, Roles and access | Roles, profiles/permission sets, sharing, SSO/MFA, field/record access and approval authority. | Sales users should see sales-related information. Finance users should see appropriate financial information. Sensitive pricing/contract information should be restricted. Users should only see records they are allowed to see. SSO/MFA and user provisioning need to follow DeepHealth standards. GDPR/data-residency requirements need to be confirmed.
Data Model Harmonization | Objects, fields, record types, relationships, identifiers, reference data and data dictionary. | Which Gleamer objects will move to NOVA? Which objects need to be transformed? Which fields have an equivalent in NOVA? Which fields don't have an equivalent? Which fields are still actually being used? Which picklist values need to be standardized? How will Account, Contact, Opportunity, Contract, Subscription, Asset, Case etc. relate to each other? | We need to compare the Gleamer Salesforce data structure with the NOVA/DeepHealth data structure and decide how they should fit togetherUnderstand Gleamer's existing data structure → compare it with NOVA → decide what the new structure should be → create field/object mappings → make sure the data can be migrated correctly.
Sales & Commercial | Account/Contact/Opportunity alignment to NOVA, pipeline, forecasting, partner/distributor scenarios. |  | Make sure all Gleamer customers and contacts are correctly represented in the new Salesforce systemOverall meaning The goal is to make sure that when Gleamer's customer and contact data is moved to NOVA, the relationships and ownership are still correct. In simple terms: We need to decide how Gleamer's Accounts and Contacts should be represented in NOVA, including their type, hierarchy, ownership, IDs, relationships, and duplicates. BR-03.01 – Account type mapping Requirement: Define how Gleamer's Account record types should map to NOVA. Gleamer currently has these record types mentioned in the document: - Lead Account - Client - Distributor - Technical Partner The requirement is to decide what each of these should become in NOVA. For example, we need to determine: Gleamer Client → What is the correct NOVA classification? The document specifically says not to simply carry the Gleamer labels into NOVA without deciding what they mean there. Expected result: Every migrated Account must have a valid classification in NOVA. Simple meaning: Decide what type each Gleamer customer/account should be in NOVA. BR-03.02 – Parent/Child Account hierarchy Requirement: Define how Account relationships should work. The requirement specifically mentions: - Group customers - Legal entities - Distributor relationships - Parent-level commercial visibility So we need to determine which Accounts are parents and which are children, and how these relationships should be represented in NOVA. Expected result: When migrated, the important Account hierarchies should still be correct. Simple meaning: Make sure related companies/accounts are connected correctly after migration. BR-03.03 – Contact relationships Requirement: Define how Contacts should be related to Accounts. The document specifically says that Contacts may relate to multiple Accounts. Therefore, we need to define how this relationship should be represented in NOVA and what Contact Roles are required. Expected result: The required Account–Contact relationships are preserved after migration. Simple meaning: Make sure every important Contact is connected to the correct Account(s) in NOVA. BR-03.04 – Ownership, territory and account team Requirement: Define who should own each migrated Account and Contact. It includes: - Ownership - Territory/region - Account team The target is to use the approved NOVA ownership model. Expected result: 100% of active Day-1 customer records should have valid ownership. Simple meaning: After migration, every active customer should have the correct owner/team/region assigned. BR-03.05 – Customer identifiers Requirement: Define how customer IDs should work in NOVA. The requirement specifically mentions: - Customer identifiers - Enterprise Account ID - Source-of-truth rules So the team needs to decide which identifier should be used and which system/data source is considered authoritative. Expected result: Every active migrated customer has the required target identifier. Simple meaning: Give every migrated customer the correct ID and clearly define which source is considered the correct source for that customer information. BR-03.06 – Duplicate/matching rules Requirement: Define how duplicate Accounts should be identified and handled. But there is an important point here: not every similar Account should automatically be merged. The requirement specifically mentions valid: - Parent/child structures - Distributor structures Therefore, the business needs to distinguish between: Actual duplicate → resolve/merge according to approved rules and Valid separate Account relationship → keep it Expected result: Duplicate candidates must either be resolved or explicitly approved as exceptions before the final migration. Simple meaning: Find duplicate customers, decide which ones should be resolved, and make sure valid separate Accounts aren't incorrectly merged. In very simple terms The entire requirement is asking six questions: Requirement Simple question BR-03.01 What type of customer is this in NOVA? BR-03.02 Which Accounts are related to each other? BR-03.03 Which Contacts belong to which Accounts? BR-03.04 Who owns each customer/account? BR-03.05 What is the correct customer ID/source of truth? BR-03.06 Which records are duplicates and which are legitimately separate? Overall objective Gleamer customer data → cleanly mapped → correctly classified → correct hierarchy → correct Contacts → correct ownership → correct IDs → duplicates resolved → ready for NOVA.
CPQ / Pricing / Quoting | Products, price books, currencies, pricing, discounts, approvals, quotes, contracts, subscriptions, renewals/overages and assets/install base. | What products and SKUs should be included in Day-1, and which products are duplicates or already available in NOVA? How should products, product families, bundles, options, dependencies, and required attributes be structured? How should pricing work across different regions and currencies? What contract terms, quantities, units, trial periods, dates, ramps, terms, and usage/overage details are needed for quoting? What discount limits and approval rules should be followed? What are the rules for the Primary Quote, quote status, versions, revisions, and approvals? How should historical pricing and commercial values be migrated when they were not created through CPQ?
Contracts & Documents | NOVA CPQ + Conga and applicable Ironclad touchpoints required for Day-1 commercial continuity. | When the contract is created How Gleamer product information becomes Subscription/Asset information Trial → Paying process Cancellation Renewal Overage/usage Go-live date Amendments Replacement Churn- Which documents are required - Which templates should be reused - What information goes into each document - Standard vs non-standard contracts - When Ironclad is triggered - How signatures/status come back - Where the final document is stored - How amendments and versions are handled
Billing / Orders | Salesforce → MuleSoft → NetSuite Day-1 order/billing handoff and status/error handling. | Salesforce → MuleSoft → NetSuite What information needs to be sent? For example: - Customer - Product/SKU - Quantity - Price - Currency - Contract term - Billing frequency - Start/end date - Tax We also need to handle: - Create - Update - Amend - Cancel - Retry - Duplicate prevention - Errors - Reconciliation
Service Transition | Salesforce-side data/configuration and Salesforce ↔ MuleSoft ↔ JSM touchpoints for Day-1 service continuity. | What happens in Salesforce? What happens in JSM? What customer information goes to JSM? What contract/subscription/asset information is required? When should Salesforce create/update a JSM ticket? What information comes back from JSM? What happens to existing open Cases? | Decide how customer support will work between Salesforce and JSM and make sure both systems have the information they need
Data Migration | Agreed Accounts, Contacts, Products, Price Books, Opportunities, Quotes, Contracts, Subscriptions where applicable, Assets, Cases and approved history/files | We need to decide: - Which Accounts to migrate - Which Contacts - Which Opportunities - Which Products - Which Contracts - Which files/documents - How much historical data to migrate - What should be excluded - How duplicates will be handled - How relationships will be preserved
Testing / Cutover / Enablement | SIT/UAT, migration rehearsals, cutover, smoke tests, hypercare, reporting and train-the-trainer enablement.

## MissingReq
Gap
Lead management is not covered. The Sales Assessment 2 (14 July) covers lead handling, qualification and enrichment. No BR covers Leads, lead-to-account conversion, lead assignment or lead scoring. Section 3 also leaves Leads and Campaigns out of the migration scope list.